## Overview
Metric | Value
Project | EduShop E-Commerce QA
Source | Jira bug export
Total Bugs | 26
Manual / UI | 18
API | 8
Status | 26 To Do
Note | Bug classification inferred from issue summaries; original descriptions retained.
Evidence | Attachment references preserved; binary attachments not included in CSV.

## All Bug Reports
Bug ID | Type | Summary | Severity | Priority | Status | Description / Reproduction Evidence | Environment | Created | Updated | Attachments / Evidence References
SCRUM-46 | Manual / UI | Admin cannot create a product with zero stock despite valid product data | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → [Admin] Create a product. Stock must be zero or greater. Preconditions: # EduShop is running. # The Admin is signed in. # The Electronics category exists. Steps to Reproduce: # Open Admin → Products. # Open the Add Product form. # Enter the following data: Name: Mustafa Zero Stock Test Description: Product zero stock validation test. Price: 10 Stock: 0 Category: Electronics Discount Percentage: 0 Image URL: Leave empty. # Click Save. # Check the Products table for the new product. Expected Result: The product is created successfully because stock 0 is valid. Actual Result: The product was not created or added to the Products table. The form remained open, and no error message explained why saving was blocked. Test Type: Manual UI testing. {noformat}Related Test Case: SCRUM-T40 Test Case Name: Verify an Admin can create a product with zero stock{noformat} |  | 09/Oct/26 2:20 PM | 09/Oct/26 2:20 PM | 09/Oct/26 2:18 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-111841.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10001
SCRUM-47 | Manual / UI | Admin can save a negative stock value when editing a product | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → [Admin] Edit a product. Editing must enforce the same validation as creating. Negative stock must be rejected and must not be saved. Preconditions: # EduShop is running. # The Admin is signed in. # Mustafa Updated Test Product exists with valid product data. Steps to Reproduce: # Open Admin → Products. # Edit Mustafa Updated Test Product. # Keep all other fields unchanged and valid. # Set Stock to -1. # Click Save. # Reopen the product and check its stock. Expected Result: The negative stock value is rejected. The product's previous stock value remains unchanged. Actual Result: The edit was saved successfully. Reopening the product confirmed that Stock was saved as -1. Test Type: Manual UI testing. Related Test Case: SCRUM-T48 Test Case Name: Verify product editing is blocked when stock is negative |  | 09/Oct/26 2:28 PM | 09/Oct/26 2:28 PM | 09/Oct/26 2:28 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-112804.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10003
SCRUM-48 | Manual / UI | Deleted product detail page is blank instead of displaying a clear not-found state | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → View product detail. Opening a removed product's detail page must display a clean not-found state. Preconditions: # EduShop is running. # Product ID 29 has been removed by the Admin. # Its original detail URL is known. Steps to Reproduce: # Open the application. # Navigate directly to [http://localhost:4200/products/29.¦http://localhost:4200/products/29.] # Inspect the product detail page. Expected Result: A clear not-found state is displayed for the removed product. Actual Result: The product detail page appeared blank without a clear not-found message. Test Type: Manual UI testing. Related Test Case: SCRUM-T61 Test Case Name: Verify a removed product disappears from the storefront |  | 09/Oct/26 2:32 PM | 09/Oct/26 2:32 PM | 09/Oct/26 2:32 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-113232.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10005
SCRUM-49 | Manual / UI | Admin can delete a category with active products without a specific warning or restriction | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Category Management → [Admin] Delete a category. Deleting a category with active products must warn the Admin or block deletion. Preconditions: # EduShop is running. # The Admin is signed in. # Mustafa Test Category contains the active product Mustafa Updated Test Product. Steps to Reproduce: # Open Admin → Categories. # Delete Mustafa Test Category. # Inspect the confirmation prompt. # Confirm deletion. # Check the Categories list and the product listing. Expected Result: Deletion is blocked, or the Admin receives a warning that the category contains active products before proceeding. Actual Result: Only the generic confirmation "Delete this category?" appeared, without mentioning active products. After confirmation, the category disappeared while its active product remained visible in the storefront. Test Type: Manual UI testing. Related Test Case: SCRUM-T68 Test Case Name: Verify deleting a category with active products is blocked or displays a warning |  | 09/Oct/26 2:40 PM | 09/Oct/26 2:40 PM | 09/Oct/26 2:40 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114021.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10007
SCRUM-50 | Manual / UI | Adding an existing cart product allows the combined quantity to exceed stock | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Add a product to the cart. The stock check must validate the combined cart quantity, not only the quantity being added. Preconditions: # EduShop is running. # A Customer is signed in. # Mustafa Updated Test Product has stock 5. # The Customer's cart contains 3 units of this product. Steps to Reproduce: # Open the product detail page. # Select quantity 3. # Add the product to the cart again. # Open the cart and inspect the resulting quantity. Expected Result: The addition is rejected because the combined quantity would be 6, exceeding stock 5. The existing cart quantity remains 3. Actual Result: The addition was accepted, and the existing cart line increased to quantity 6 despite stock being 5. Test Type: Manual UI testing. Related Test Case: SCRUM-T71 Test Case Name: Verify adding a product is blocked when the combined cart quantity exceeds stock |  | 09/Oct/26 2:42 PM | 09/Oct/26 2:42 PM | 09/Oct/26 2:42 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114230.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10010 09/Oct/26 2:42 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114237.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10011
SCRUM-51 | Manual / UI | Updating a cart item's quantity allows it to exceed the product stock | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Update quantity or remove a line. The quantity set on an existing cart line must respect the product's current stock as a ceiling. Preconditions: # EduShop is running. # A Customer is signed in. # Mustafa Updated Test Product has stock 5. # The product is already in the Customer's cart. Steps to Reproduce: # Open Cart. # Set the product quantity to 5. # Increase the quantity from 5 to 6. # Inspect the resulting cart quantity. Expected Result: Increasing the quantity to 6 is blocked because stock is 5. The quantity remains 5. Actual Result: The cart accepted quantity 6 although the product's stock was 5. Test Type: Manual UI testing. Related Test Case: SCRUM-T72 Test Case Name: Verify cart quantity updates are blocked when the requested quantity exceeds stock |  | 09/Oct/26 2:44 PM | 09/Oct/26 2:44 PM | 09/Oct/26 2:44 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114416.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10014 09/Oct/26 2:44 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114422.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10015
SCRUM-52 | Manual / UI | Cart and checkout totals are incorrect when a product quantity exceeds 10 | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Cart totals are always arithmetically correct. Each line subtotal must equal discounted unit price multiplied by quantity for all quantities from 1 to 100. The cart total and item-count badge must agree. Preconditions: # EduShop is running. # A Customer is signed in. # The cart contains only Mustafa Updated Test Product. # The product price is $20.00, with a 10% discount. # The discounted unit price is $18.00. # Sufficient stock is available. Steps to Reproduce: # Set the cart quantity to 10. # Confirm the subtotal and total are $180.00. # Increase the quantity to 11. # Inspect the quantity, cart badge, subtotal, and total. # Refresh the cart. # Open Checkout and inspect its total. Expected Result: For quantity 11, the subtotal, cart total, and checkout total are $198.00 ($18.00 × 11). The cart badge displays 11. Actual Result: The quantity and cart badge displayed 11, but the subtotal and cart total remained $180.00. The incorrect total persisted after refreshing and appeared in Checkout. Additional Observations: Quantity 12 displayed $198.00 instead of $216.00. Quantity 100 displayed $1782.00 instead of $1800.00. Order #4, placed with quantity 11, correctly showed $198.00 in My Orders. The observed error affected the cart and checkout preview totals. Test Type: Manual UI testing. Related Test Case: SCRUM-T73 Test Case Name: Verify cart totals are correct for a product quantity greater than 10 Additional Related Test Case: SCRUM-T84 Test Case Name: Verify the order total is correct when a product quantity exceeds 10 |  | 09/Oct/26 2:46 PM | 09/Oct/26 2:49 PM | 09/Oct/26 2:46 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114614.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10018 09/Oct/26 2:46 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114621.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10019
SCRUM-53 | Manual / UI | Checkout does not display the required fields or instructions for the selected payment method | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Checkout & Orders → Check out. Selecting a payment method must reveal the fields or instructions required for that method. Preconditions: # EduShop is running. # A Customer is signed in. # The Customer has a non-empty cart. Steps to Reproduce: # Open Checkout. # Select Credit/Debit Card and inspect the form. # Select PayPal and inspect the form. # Select Bank Transfer and inspect the form. Expected Result: Card displays card number, expiry, and CVV fields. PayPal displays a note explaining that the Customer will be redirected. Bank Transfer displays account/reference details. Actual Result: The form did not display the required card fields, PayPal redirection note, or Bank Transfer account/reference details when those methods were selected. Test Type: Manual UI testing. Related Test Case: SCRUM-T81 Test Case Name: Verify checkout displays the required fields or instructions for each payment method |  | 09/Oct/26 2:51 PM | 09/Oct/26 2:51 PM | 09/Oct/26 2:50 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115035.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10025 09/Oct/26 2:50 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115048.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10026 09/Oct/26 2:51 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115100.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10027 09/Oct/26 2:51 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115109.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10028 09/Oct/26 2:51 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115116.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10029
SCRUM-54 | Manual / UI | Cart badge retains the previous item count after successful checkout | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Cart icon reflects reality immediately. The cart badge must reflect the current cart contents. Checkout & Orders → Check out. The cart must be emptied after a successful order. Preconditions: # EduShop is running. # A Customer is signed in. # The cart contains 2 units of a product, and the cart badge displays 2. Steps to Reproduce: # Open Checkout. # Enter a valid shipping address. # Select Cash on Delivery. # Click Place Order. # Inspect the cart badge on the order confirmation page. # Navigate to My Orders and inspect the badge again. # Open Cart and check its contents. Expected Result: After successful checkout, the cart is empty and the badge immediately stops displaying the previous count of 2. Actual Result: Order #3 was placed successfully, but the cart badge still displayed 2 on the confirmation page. The count disappeared only after navigating to My Orders. The cart itself was empty. Test Type: Manual UI testing. Related Test Case: SCRUM-T83 Test Case Name: Verify successful checkout creates an order, clears the cart, and decreases stock |  | 09/Oct/26 2:54 PM | 09/Oct/26 2:54 PM | 09/Oct/26 2:54 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115416.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10031
SCRUM-55 | Manual / UI | Customers can submit product reviews without a Delivered purchase | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Reviews & Ratings → Submit a review. A Customer may review a product only if they have received it through a completed order, such as an order with status Delivered. Scenario 1 — No purchase: Preconditions: Customer [Test@gmail.com¦mailto:Test@gmail.com] has never ordered Wireless Bluetooth Headphones and has not reviewed it before. Steps: # Sign in as this Customer. # Open Wireless Bluetooth Headphones. # Select rating 5. # Enter: This review tests whether a Customer who never purchased the product can submit a review. # Submit the review. # Refresh the product page. Actual Result: The review was accepted and remained visible after refreshing under Mustafa Test. Scenario 2 — Purchase not delivered: Preconditions: Customer [mustafa@gmail.com¦mailto:mustafa@gmail.com] has order #6 containing Yoga Mat Premium with status Processing, no Delivered order containing that product, and no previous review for it. Steps: # Sign in as this Customer. # Open Yoga Mat Premium. # Select rating 4. # Enter: This review tests submission before the product has been delivered. # Submit the review. # Refresh the product page. Actual Result: The review was accepted and remained visible after refreshing. Expected Result: Both review attempts are rejected with a clear message. Neither review is saved because the Customer has no Delivered purchase of the reviewed product. Test Type: Manual UI testing. Related Test Case: SCRUM-T92 Test Case Name: Verify a Customer cannot review a product they have never purchased Additional Related Test Case: SCRUM-T96 Test Case Name: Verify a Customer cannot review a product from a Processing order |  | 09/Oct/26 5:32 PM | 09/Oct/26 5:32 PM | 09/Oct/26 5:30 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-143039.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10034 09/Oct/26 5:31 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-143154.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10035
SCRUM-56 | Manual / UI | Submitting a second review for the same product does not display a clear rejection message | Low | Medium | To Do | Requirement: EduShop Test Backlog → Product Reviews & Ratings → Submit a review. A second review from the same user for the same product must be rejected with a clear message. Preconditions: # EduShop is running. # Customer [Test@gmail.com¦mailto:Test@gmail.com] is signed in. # This Customer already has a saved review for Wireless Bluetooth Headphones. Steps to Reproduce: # Open Wireless Bluetooth Headphones. # Confirm the Customer's original review is displayed. # Select rating 4. # Enter: This is a second review attempt for the same product. # Submit the review. # Refresh the page and inspect the reviews. Expected Result: The second review is rejected with a clear message explaining that the Customer has already reviewed this product. Only the original review remains. Actual Result: The second review was not saved, but no rejection message appeared. After refreshing, only the original review remained. Test Type: Manual UI testing. |  | 09/Oct/26 6:35 PM | 09/Oct/26 6:35 PM | 09/Oct/26 6:35 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-153543.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10037
SCRUM-57 | Manual / UI | Wishlist header does not display or update the saved product count | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Wishlist. The site header must display the number of wishlisted products next to the Wishlist icon, and the count must update immediately when an item is added or removed. Preconditions: # EduShop is running. # Customer [mustafa@gmail.com¦mailto:mustafa@gmail.com] is signed in. Steps to Reproduce: # Open Wishlist and confirm it is empty. # Add Mechanical Keyboard to the wishlist from the product listing. # Inspect the Wishlist icon in the header. # Add Yoga Mat Premium from its product detail page. # Inspect the Wishlist icon in the header again. # Remove Mechanical Keyboard from Wishlist. # Inspect the Wishlist icon in the header again. Expected Result: The header displays count 1 after the first addition, 2 after the second addition, and 1 after removing Mechanical Keyboard. Actual Result: Products were added and removed successfully, but no wishlist count appeared next to the Wishlist icon in the header at any time. Test Type: Manual UI testing. |  | 09/Oct/26 6:40 PM | 09/Oct/26 6:40 PM | 09/Oct/26 6:38 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-153856.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10040 09/Oct/26 6:39 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-153945.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10041
SCRUM-58 | Manual / UI | Admin dashboard does not display the active category count | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Admin Dashboard & Reporting → View store overview. The dashboard must display the total number of active categories. Preconditions: # EduShop is running. # An Admin is signed in. # Active categories exist in the store. Steps to Reproduce: # Sign in as an Admin. # Open Admin Dashboard. # Inspect the dashboard overview metrics. Expected Result: The dashboard displays the active category count. Actual Result: The dashboard displayed Total Users, Total Orders, Total Products, Total Revenue, Monthly Revenue, Pending Orders, and Low Stock Products. No active category count was displayed. Test Type: Manual UI testing. Related Test Case: SCRUM-T103 Test Case Name: Verify the Admin dashboard displays all required store overview information |  | 09/Oct/26 6:43 PM | 09/Oct/26 6:43 PM
SCRUM-59 | Manual / UI | Admin dashboard does not display the top-selling products section | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Admin Dashboard & Reporting → View store overview. The dashboard must display the top 5 best-selling products. Preconditions: # EduShop is running. # An Admin is signed in. # Orders containing products exist in the store. Steps to Reproduce: # Sign in as an Admin. # Open Admin Dashboard. # Scroll through the complete dashboard page. # Inspect the available sections. Expected Result: The dashboard displays a Top Products section showing the top 5 best-selling products, or all qualifying products if fewer than 5 exist. Actual Result: No Top Products or best-selling products section was displayed anywhere on the Admin Dashboard. Test Type: Manual UI testing. Related Test Case: SCRUM-T103 Test Case Name: Verify the Admin dashboard displays all required store overview information |  | 09/Oct/26 6:44 PM | 09/Oct/26 6:44 PM
SCRUM-60 | Manual / UI | Admin console does not provide access to the dedicated revenue report | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Admin Dashboard & Reporting → View the revenue report. An Admin must be able to access the revenue report from inside the Admin console through a tab, link, or section. Preconditions: # EduShop is running. # An Admin is signed in. Steps to Reproduce: # Open Admin Dashboard. # Inspect the side navigation and all dashboard sections. # Inspect the Total Revenue and Monthly Revenue cards for navigation. # Attempt to locate and open a dedicated revenue report. Expected Result: A link, tab, or section is available in the Admin console to open the dedicated revenue report. Actual Result: No link, tab, section, or clickable dashboard element was available to access the revenue report. Only summary revenue values were displayed. Test Type: Manual UI testing. |  | 09/Oct/26 6:45 PM | 09/Oct/26 6:45 PM
SCRUM-61 | Manual / UI | Dashboard Total Revenue omits decimal amounts from the displayed total | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Admin Dashboard & Reporting → View store overview. The dashboard must display total revenue consistently and accurately. Preconditions: # EduShop is running. # An Admin is signed in. # Orders exist with non-cancelled totals that include decimal values. Steps to Reproduce: # Open Admin → Orders and record the amount and status of each order. # Sum all non-cancelled order amounts. # Open Admin Dashboard and inspect Total Revenue. # Change order #5 with amount $75.99 from Pending to Cancelled. # Refresh the dashboard and inspect Total Revenue again. Expected Result: Total Revenue displays the exact calculated amount including decimals. Before cancellation: $1957.41. After cancelling order #5: $1881.42. Actual Result: The dashboard omitted the decimal amounts. Before cancellation, it displayed $1957 instead of $1957.41. After cancelling order #5, it displayed $1881 instead of $1881.42. Monthly Revenue displayed the correct decimal values. Test Type: Manual UI testing. |  | 09/Oct/26 6:47 PM | 09/Oct/26 6:47 PM | 09/Oct/26 6:47 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-154719.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10043
SCRUM-62 | Manual / UI | Product detail page does not provide an option for a Customer to delete their own review | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Reviews & Ratings → Delete a review. Only the review's own author, or an Admin, can delete it. Preconditions: # EduShop is running. # Customer [mustafa@gmail.com¦mailto:mustafa@gmail.com] is signed in. # The Customer has a saved review for Yoga Mat Premium. Steps to Reproduce: # Open the Yoga Mat Premium product detail page. # Locate the Customer's own saved review. # Inspect the review actions. Expected Result: The Customer can access a delete option for their own review. Actual Result: The Customer's review was displayed, but no Delete button, delete icon, or other removal option was available. Test Type: Manual UI testing. Related Test Case: SCRUM-T97 Test Case Name: Verify a Customer can delete their own review |  | 09/Oct/26 6:52 PM | 09/Oct/26 6:52 PM | 09/Oct/26 6:52 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-155220.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10045
SCRUM-63 | Manual / UI | Admin console does not provide an option to edit or rename an existing category | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Category Management → [Admin] Rename a category. An Admin must be able to edit an existing category to correct or rename it. Preconditions: # EduShop is running. # An Admin is signed in. # Existing categories are available. Steps to Reproduce: # Open Admin → Categories. # Inspect the available actions for an existing category. Expected Result: An Edit or Rename option is available, allowing the Admin to update an existing category. Actual Result: No Edit or Rename option was available for categories. Only the delete action was displayed, so category renaming could not be performed from the Admin console. Test Type: Manual UI testing. |  | 09/Oct/26 7:03 PM | 09/Oct/26 7:03 PM | 09/Oct/26 7:03 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Screenshot 2026-10-09 185640.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10047
SCRUM-64 | API | API category filter is case-sensitive and returns no products for lowercase category values | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → Search and filter products. Filtering by category name must be case-insensitive. Electronics, electronics, and ELECTRONICS must return the same matching products. Preconditions: # EduShop backend is running. # Active products exist in the Electronics category. # The API is accessible at [http://localhost:5000.¦http://localhost:5000.] Steps to Reproduce: # Send GET /api/product?Category=Electronics. # Note that the response returns 200 OK with totalCount: 6. # Send GET /api/product?Category=electronics. Expected Result: The lowercase category filter returns 200 OK with the same six Electronics products and totalCount: 6. Actual Result: The request returned 200 OK but returned an empty items array with totalCount: 0. Affected Endpoint: GET /api/product?Category=electronics Test Type: API Testing. Related Test Case: SCRUM-T113 - API - Verify product category filtering is case-insensitive |  | 10/Oct/26 3:53 PM | 10/Oct/26 3:53 PM | 10/Oct/26 3:53 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 1_Products - Category Filter - electronics (Lowercase).png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10049
SCRUM-65 | API | API accepts negative stock values when updating a product | High | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → [Admin] Edit a product. Editing a product must enforce the same validation as creating it. Stock must be zero or greater, and a negative Stock value must be rejected with 400 Bad Request. Preconditions: # EduShop backend is running. # An Admin access token is available. # Product ID 26 exists. Steps to Reproduce: # Send an authenticated Admin PUT request to /api/product/26. # Use valid product data with "Stock": -1. Expected Result: The API returns 400 Bad Request and does not save a negative stock value. Actual Result: The API returned 200 OK and saved the product with Stock: -1. Affected Endpoint: PUT /api/product/26 Test Type: API Testing. Related Test Case: SCRUM-T114 - API - Verify product update rejects negative stock |  | 10/Oct/26 3:58 PM | 10/Oct/26 3:58 PM | 10/Oct/26 3:58 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 2_Product Update - Negative Stock Rejected.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10051
SCRUM-66 | API | API allows Customers to submit reviews for products they have not purchased | High | Medium | To Do | Requirement: EduShop Test Backlog → Product Reviews & Ratings → Submit a review. A Customer may review only a product they have purchased in an order whose status is Delivered. Preconditions: # EduShop backend is running. # A Customer access token is available. # The Customer has no Delivered order containing Product ID 16. Steps to Reproduce: # Send a Customer-authenticated POST request to /api/review. # Use the following request data: ProductId: 16 Rating: 5 Comment: API test: customer has not purchased this product. Expected Result: The API returns 400 Bad Request with a clear message, and no review is created. Actual Result: The API returned 200 OK and created a review even though the Customer has no Delivered order containing Product ID 16. The test review was deleted afterward as test-data cleanup. Affected Endpoint: POST /api/review Test Type: API Testing. Related Test Case: SCRUM-T115 - API - Verify a Customer cannot review an unpurchased product |  | 10/Oct/26 4:04 PM | 10/Oct/26 4:04 PM | 10/Oct/26 4:04 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 3_Review - Unpurchased Product Rejected.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10053
SCRUM-67 | API | API allows an Admin to rename a category to an existing category name | High | Medium | To Do | Requirement: EduShop Test Backlog → Category Management → [Admin] Rename a category. The same duplicate-name rule that applies on category creation must apply when renaming a category. Renaming a category to a name that already exists must be rejected. Preconditions: # EduShop backend is running. # An Admin access token is available. # Category ID 2 exists with the name Clothing. # Another category already exists with the name Electronics. Steps to Reproduce: # Send an Admin-authenticated PUT request to /api/category/2. # Use a request body with Name set to Electronics. Expected Result: The API returns 400 Bad Request with a clear duplicate-name message, and Category ID 2 remains named Clothing. Actual Result: The API returned 200 OK and changed Category ID 2 from Clothing to Electronics, creating a duplicate category name. The category was restored to Clothing afterward as test-data cleanup. Affected Endpoint: PUT /api/category/2 Test Type: API Testing. Related Test Case: SCRUM-T116 - API - Verify category update rejects a duplicate name |  | 10/Oct/26 4:07 PM | 10/Oct/26 4:07 PM | 10/Oct/26 4:07 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 4 _Category Update - Duplicate Name Rejected.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10055
SCRUM-68 | API | API calculates incorrect cart subtotal and total amount for quantities greater than 10 | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Cart totals are always arithmetically correct. Every line subtotal must equal the discounted unit price multiplied by the line quantity, for any quantity from 1 to 100. The cart total must equal the sum of line subtotals. Preconditions: # EduShop backend is running. # A Customer access token is available. # The Customer cart is empty. # Product ID 2 is active with a price of 249.99, a 15% discount, and at least 49 units in stock. Steps to Reproduce: # Send a Customer-authenticated POST request to /api/cart/items. # Use the request body: ProductId: 2 Quantity: 49 # Inspect the returned cart totals. Expected Result: The discounted unit price is 212.49. For quantity 49, the line subtotal and totalAmount should be 10412.08, and totalItems should be 49. Actual Result: The API returned 200 OK with totalItems: 49, but the subtotal and totalAmount were 10199.59. This amount equals the price of 48 units instead of 49 units. Affected Endpoint: POST /api/cart/items Test Type: API Testing. Related Test Case: [117] |  | 10/Oct/26 4:11 PM | 10/Oct/26 4:11 PM | 10/Oct/26 4:10 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 5 _Cart - Add Product Up To Available Stock.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10057
SCRUM-69 | API | API allows cart quantity to exceed stock when adding to an existing cart line | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Add a product to the cart. The stock check must validate the combined quantity already in the cart plus the newly added quantity. A cart quantity must not exceed the product's current stock. Preconditions: # EduShop backend is running. # A Customer access token is available. # The Customer cart is empty. # Product ID 2 has 49 units in stock. Steps to Reproduce: # Send a Customer-authenticated POST request to /api/cart/items with ProductId 2 and Quantity 49. # Send the same request again with ProductId 2 and Quantity 2. # Inspect the returned cart. Expected Result: The second request returns 400 Bad Request with an insufficient-stock message. The cart remains at quantity 49. Actual Result: The second request returned 200 OK and increased the cart quantity to 51, exceeding the available stock of 49. Affected Endpoint: POST /api/cart/items Test Type: API Testing. Related Test Case: [118] |  | 10/Oct/26 4:14 PM | 10/Oct/26 4:14 PM
SCRUM-70 | API | API allows updating a cart item quantity beyond available stock | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Update quantity or remove a line. The quantity set on an existing cart line must respect the product's current stock as a ceiling. Preconditions: # EduShop backend is running. # A Customer access token is available. # The Customer cart contains one unit of Product ID 2. # Product ID 2 has 49 units in stock. # The cart item ID for Product ID 2 is available. Steps to Reproduce: # Send a Customer-authenticated PUT request to /api/cart/items/{cartItemId}. # Use the request body: Quantity: 50 # Inspect the returned cart. Expected Result: The API returns 400 Bad Request with an insufficient-stock message. The item quantity remains unchanged. Actual Result: The API returned 200 OK and changed the cart item quantity to 50, exceeding the available stock of 49. Affected Endpoint: PUT /api/cart/items/{cartItemId} Test Type: API Testing. Related Test Case: [SCRUM-T119] |  | 10/Oct/26 4:16 PM | 10/Oct/26 4:16 PM | 10/Oct/26 4:16 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 7_Cart Item - Quantity Above Stock Rejected.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10059
SCRUM-71 | API | Customer order retrieval returns empty userEmail and userName | Medium | Medium | To Do | Environment: EduShop API – Postman Base URL: [http://localhost:5000¦http://localhost:5000] Precondition: A Customer account has a successfully created order. The tested order ID was 9. Steps to Reproduce: # Log in as a Customer and obtain a valid access token. # Send GET /api/order using the Customer token. # Locate the created order in the response. # Send GET /api/order/9 using the same Customer token. # Check the userEmail and userName fields in both responses. Expected Result: Both endpoints return the created order with populated userEmail and userName fields in the OrderDto response. Actual Result: Both endpoints return 200 OK and the correct order details, but userEmail and userName are returned as empty strings (""). Affected Endpoints: GET /api/order GET /api/order/{id} |  | 11/Oct/26 4:22 PM | 11/Oct/26 4:22 PM | 11/Oct/26 4:21 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Orders - Customer Lists Own Orders.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10061

## Manual UI Bugs
Bug ID | Type | Summary | Severity | Priority | Status | Description / Reproduction Evidence | Environment | Created | Updated | Attachments / Evidence References
SCRUM-46 | Manual / UI | Admin cannot create a product with zero stock despite valid product data | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → [Admin] Create a product. Stock must be zero or greater. Preconditions: # EduShop is running. # The Admin is signed in. # The Electronics category exists. Steps to Reproduce: # Open Admin → Products. # Open the Add Product form. # Enter the following data: Name: Mustafa Zero Stock Test Description: Product zero stock validation test. Price: 10 Stock: 0 Category: Electronics Discount Percentage: 0 Image URL: Leave empty. # Click Save. # Check the Products table for the new product. Expected Result: The product is created successfully because stock 0 is valid. Actual Result: The product was not created or added to the Products table. The form remained open, and no error message explained why saving was blocked. Test Type: Manual UI testing. {noformat}Related Test Case: SCRUM-T40 Test Case Name: Verify an Admin can create a product with zero stock{noformat} |  | 09/Oct/26 2:20 PM | 09/Oct/26 2:20 PM | 09/Oct/26 2:18 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-111841.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10001
SCRUM-47 | Manual / UI | Admin can save a negative stock value when editing a product | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → [Admin] Edit a product. Editing must enforce the same validation as creating. Negative stock must be rejected and must not be saved. Preconditions: # EduShop is running. # The Admin is signed in. # Mustafa Updated Test Product exists with valid product data. Steps to Reproduce: # Open Admin → Products. # Edit Mustafa Updated Test Product. # Keep all other fields unchanged and valid. # Set Stock to -1. # Click Save. # Reopen the product and check its stock. Expected Result: The negative stock value is rejected. The product's previous stock value remains unchanged. Actual Result: The edit was saved successfully. Reopening the product confirmed that Stock was saved as -1. Test Type: Manual UI testing. Related Test Case: SCRUM-T48 Test Case Name: Verify product editing is blocked when stock is negative |  | 09/Oct/26 2:28 PM | 09/Oct/26 2:28 PM | 09/Oct/26 2:28 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-112804.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10003
SCRUM-48 | Manual / UI | Deleted product detail page is blank instead of displaying a clear not-found state | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → View product detail. Opening a removed product's detail page must display a clean not-found state. Preconditions: # EduShop is running. # Product ID 29 has been removed by the Admin. # Its original detail URL is known. Steps to Reproduce: # Open the application. # Navigate directly to [http://localhost:4200/products/29.¦http://localhost:4200/products/29.] # Inspect the product detail page. Expected Result: A clear not-found state is displayed for the removed product. Actual Result: The product detail page appeared blank without a clear not-found message. Test Type: Manual UI testing. Related Test Case: SCRUM-T61 Test Case Name: Verify a removed product disappears from the storefront |  | 09/Oct/26 2:32 PM | 09/Oct/26 2:32 PM | 09/Oct/26 2:32 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-113232.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10005
SCRUM-49 | Manual / UI | Admin can delete a category with active products without a specific warning or restriction | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Category Management → [Admin] Delete a category. Deleting a category with active products must warn the Admin or block deletion. Preconditions: # EduShop is running. # The Admin is signed in. # Mustafa Test Category contains the active product Mustafa Updated Test Product. Steps to Reproduce: # Open Admin → Categories. # Delete Mustafa Test Category. # Inspect the confirmation prompt. # Confirm deletion. # Check the Categories list and the product listing. Expected Result: Deletion is blocked, or the Admin receives a warning that the category contains active products before proceeding. Actual Result: Only the generic confirmation "Delete this category?" appeared, without mentioning active products. After confirmation, the category disappeared while its active product remained visible in the storefront. Test Type: Manual UI testing. Related Test Case: SCRUM-T68 Test Case Name: Verify deleting a category with active products is blocked or displays a warning |  | 09/Oct/26 2:40 PM | 09/Oct/26 2:40 PM | 09/Oct/26 2:40 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114021.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10007
SCRUM-50 | Manual / UI | Adding an existing cart product allows the combined quantity to exceed stock | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Add a product to the cart. The stock check must validate the combined cart quantity, not only the quantity being added. Preconditions: # EduShop is running. # A Customer is signed in. # Mustafa Updated Test Product has stock 5. # The Customer's cart contains 3 units of this product. Steps to Reproduce: # Open the product detail page. # Select quantity 3. # Add the product to the cart again. # Open the cart and inspect the resulting quantity. Expected Result: The addition is rejected because the combined quantity would be 6, exceeding stock 5. The existing cart quantity remains 3. Actual Result: The addition was accepted, and the existing cart line increased to quantity 6 despite stock being 5. Test Type: Manual UI testing. Related Test Case: SCRUM-T71 Test Case Name: Verify adding a product is blocked when the combined cart quantity exceeds stock |  | 09/Oct/26 2:42 PM | 09/Oct/26 2:42 PM | 09/Oct/26 2:42 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114230.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10010 09/Oct/26 2:42 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114237.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10011
SCRUM-51 | Manual / UI | Updating a cart item's quantity allows it to exceed the product stock | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Update quantity or remove a line. The quantity set on an existing cart line must respect the product's current stock as a ceiling. Preconditions: # EduShop is running. # A Customer is signed in. # Mustafa Updated Test Product has stock 5. # The product is already in the Customer's cart. Steps to Reproduce: # Open Cart. # Set the product quantity to 5. # Increase the quantity from 5 to 6. # Inspect the resulting cart quantity. Expected Result: Increasing the quantity to 6 is blocked because stock is 5. The quantity remains 5. Actual Result: The cart accepted quantity 6 although the product's stock was 5. Test Type: Manual UI testing. Related Test Case: SCRUM-T72 Test Case Name: Verify cart quantity updates are blocked when the requested quantity exceeds stock |  | 09/Oct/26 2:44 PM | 09/Oct/26 2:44 PM | 09/Oct/26 2:44 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114416.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10014 09/Oct/26 2:44 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114422.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10015
SCRUM-52 | Manual / UI | Cart and checkout totals are incorrect when a product quantity exceeds 10 | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Cart totals are always arithmetically correct. Each line subtotal must equal discounted unit price multiplied by quantity for all quantities from 1 to 100. The cart total and item-count badge must agree. Preconditions: # EduShop is running. # A Customer is signed in. # The cart contains only Mustafa Updated Test Product. # The product price is $20.00, with a 10% discount. # The discounted unit price is $18.00. # Sufficient stock is available. Steps to Reproduce: # Set the cart quantity to 10. # Confirm the subtotal and total are $180.00. # Increase the quantity to 11. # Inspect the quantity, cart badge, subtotal, and total. # Refresh the cart. # Open Checkout and inspect its total. Expected Result: For quantity 11, the subtotal, cart total, and checkout total are $198.00 ($18.00 × 11). The cart badge displays 11. Actual Result: The quantity and cart badge displayed 11, but the subtotal and cart total remained $180.00. The incorrect total persisted after refreshing and appeared in Checkout. Additional Observations: Quantity 12 displayed $198.00 instead of $216.00. Quantity 100 displayed $1782.00 instead of $1800.00. Order #4, placed with quantity 11, correctly showed $198.00 in My Orders. The observed error affected the cart and checkout preview totals. Test Type: Manual UI testing. Related Test Case: SCRUM-T73 Test Case Name: Verify cart totals are correct for a product quantity greater than 10 Additional Related Test Case: SCRUM-T84 Test Case Name: Verify the order total is correct when a product quantity exceeds 10 |  | 09/Oct/26 2:46 PM | 09/Oct/26 2:49 PM | 09/Oct/26 2:46 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114614.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10018 09/Oct/26 2:46 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-114621.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10019
SCRUM-53 | Manual / UI | Checkout does not display the required fields or instructions for the selected payment method | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Checkout & Orders → Check out. Selecting a payment method must reveal the fields or instructions required for that method. Preconditions: # EduShop is running. # A Customer is signed in. # The Customer has a non-empty cart. Steps to Reproduce: # Open Checkout. # Select Credit/Debit Card and inspect the form. # Select PayPal and inspect the form. # Select Bank Transfer and inspect the form. Expected Result: Card displays card number, expiry, and CVV fields. PayPal displays a note explaining that the Customer will be redirected. Bank Transfer displays account/reference details. Actual Result: The form did not display the required card fields, PayPal redirection note, or Bank Transfer account/reference details when those methods were selected. Test Type: Manual UI testing. Related Test Case: SCRUM-T81 Test Case Name: Verify checkout displays the required fields or instructions for each payment method |  | 09/Oct/26 2:51 PM | 09/Oct/26 2:51 PM | 09/Oct/26 2:50 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115035.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10025 09/Oct/26 2:50 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115048.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10026 09/Oct/26 2:51 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115100.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10027 09/Oct/26 2:51 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115109.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10028 09/Oct/26 2:51 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115116.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10029
SCRUM-54 | Manual / UI | Cart badge retains the previous item count after successful checkout | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Cart icon reflects reality immediately. The cart badge must reflect the current cart contents. Checkout & Orders → Check out. The cart must be emptied after a successful order. Preconditions: # EduShop is running. # A Customer is signed in. # The cart contains 2 units of a product, and the cart badge displays 2. Steps to Reproduce: # Open Checkout. # Enter a valid shipping address. # Select Cash on Delivery. # Click Place Order. # Inspect the cart badge on the order confirmation page. # Navigate to My Orders and inspect the badge again. # Open Cart and check its contents. Expected Result: After successful checkout, the cart is empty and the badge immediately stops displaying the previous count of 2. Actual Result: Order #3 was placed successfully, but the cart badge still displayed 2 on the confirmation page. The count disappeared only after navigating to My Orders. The cart itself was empty. Test Type: Manual UI testing. Related Test Case: SCRUM-T83 Test Case Name: Verify successful checkout creates an order, clears the cart, and decreases stock |  | 09/Oct/26 2:54 PM | 09/Oct/26 2:54 PM | 09/Oct/26 2:54 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-115416.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10031
SCRUM-55 | Manual / UI | Customers can submit product reviews without a Delivered purchase | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Reviews & Ratings → Submit a review. A Customer may review a product only if they have received it through a completed order, such as an order with status Delivered. Scenario 1 — No purchase: Preconditions: Customer [Test@gmail.com¦mailto:Test@gmail.com] has never ordered Wireless Bluetooth Headphones and has not reviewed it before. Steps: # Sign in as this Customer. # Open Wireless Bluetooth Headphones. # Select rating 5. # Enter: This review tests whether a Customer who never purchased the product can submit a review. # Submit the review. # Refresh the product page. Actual Result: The review was accepted and remained visible after refreshing under Mustafa Test. Scenario 2 — Purchase not delivered: Preconditions: Customer [mustafa@gmail.com¦mailto:mustafa@gmail.com] has order #6 containing Yoga Mat Premium with status Processing, no Delivered order containing that product, and no previous review for it. Steps: # Sign in as this Customer. # Open Yoga Mat Premium. # Select rating 4. # Enter: This review tests submission before the product has been delivered. # Submit the review. # Refresh the product page. Actual Result: The review was accepted and remained visible after refreshing. Expected Result: Both review attempts are rejected with a clear message. Neither review is saved because the Customer has no Delivered purchase of the reviewed product. Test Type: Manual UI testing. Related Test Case: SCRUM-T92 Test Case Name: Verify a Customer cannot review a product they have never purchased Additional Related Test Case: SCRUM-T96 Test Case Name: Verify a Customer cannot review a product from a Processing order |  | 09/Oct/26 5:32 PM | 09/Oct/26 5:32 PM | 09/Oct/26 5:30 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-143039.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10034 09/Oct/26 5:31 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-143154.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10035
SCRUM-56 | Manual / UI | Submitting a second review for the same product does not display a clear rejection message | Low | Medium | To Do | Requirement: EduShop Test Backlog → Product Reviews & Ratings → Submit a review. A second review from the same user for the same product must be rejected with a clear message. Preconditions: # EduShop is running. # Customer [Test@gmail.com¦mailto:Test@gmail.com] is signed in. # This Customer already has a saved review for Wireless Bluetooth Headphones. Steps to Reproduce: # Open Wireless Bluetooth Headphones. # Confirm the Customer's original review is displayed. # Select rating 4. # Enter: This is a second review attempt for the same product. # Submit the review. # Refresh the page and inspect the reviews. Expected Result: The second review is rejected with a clear message explaining that the Customer has already reviewed this product. Only the original review remains. Actual Result: The second review was not saved, but no rejection message appeared. After refreshing, only the original review remained. Test Type: Manual UI testing. |  | 09/Oct/26 6:35 PM | 09/Oct/26 6:35 PM | 09/Oct/26 6:35 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-153543.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10037
SCRUM-57 | Manual / UI | Wishlist header does not display or update the saved product count | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Wishlist. The site header must display the number of wishlisted products next to the Wishlist icon, and the count must update immediately when an item is added or removed. Preconditions: # EduShop is running. # Customer [mustafa@gmail.com¦mailto:mustafa@gmail.com] is signed in. Steps to Reproduce: # Open Wishlist and confirm it is empty. # Add Mechanical Keyboard to the wishlist from the product listing. # Inspect the Wishlist icon in the header. # Add Yoga Mat Premium from its product detail page. # Inspect the Wishlist icon in the header again. # Remove Mechanical Keyboard from Wishlist. # Inspect the Wishlist icon in the header again. Expected Result: The header displays count 1 after the first addition, 2 after the second addition, and 1 after removing Mechanical Keyboard. Actual Result: Products were added and removed successfully, but no wishlist count appeared next to the Wishlist icon in the header at any time. Test Type: Manual UI testing. |  | 09/Oct/26 6:40 PM | 09/Oct/26 6:40 PM | 09/Oct/26 6:38 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-153856.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10040 09/Oct/26 6:39 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-153945.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10041
SCRUM-58 | Manual / UI | Admin dashboard does not display the active category count | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Admin Dashboard & Reporting → View store overview. The dashboard must display the total number of active categories. Preconditions: # EduShop is running. # An Admin is signed in. # Active categories exist in the store. Steps to Reproduce: # Sign in as an Admin. # Open Admin Dashboard. # Inspect the dashboard overview metrics. Expected Result: The dashboard displays the active category count. Actual Result: The dashboard displayed Total Users, Total Orders, Total Products, Total Revenue, Monthly Revenue, Pending Orders, and Low Stock Products. No active category count was displayed. Test Type: Manual UI testing. Related Test Case: SCRUM-T103 Test Case Name: Verify the Admin dashboard displays all required store overview information |  | 09/Oct/26 6:43 PM | 09/Oct/26 6:43 PM
SCRUM-59 | Manual / UI | Admin dashboard does not display the top-selling products section | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Admin Dashboard & Reporting → View store overview. The dashboard must display the top 5 best-selling products. Preconditions: # EduShop is running. # An Admin is signed in. # Orders containing products exist in the store. Steps to Reproduce: # Sign in as an Admin. # Open Admin Dashboard. # Scroll through the complete dashboard page. # Inspect the available sections. Expected Result: The dashboard displays a Top Products section showing the top 5 best-selling products, or all qualifying products if fewer than 5 exist. Actual Result: No Top Products or best-selling products section was displayed anywhere on the Admin Dashboard. Test Type: Manual UI testing. Related Test Case: SCRUM-T103 Test Case Name: Verify the Admin dashboard displays all required store overview information |  | 09/Oct/26 6:44 PM | 09/Oct/26 6:44 PM
SCRUM-60 | Manual / UI | Admin console does not provide access to the dedicated revenue report | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Admin Dashboard & Reporting → View the revenue report. An Admin must be able to access the revenue report from inside the Admin console through a tab, link, or section. Preconditions: # EduShop is running. # An Admin is signed in. Steps to Reproduce: # Open Admin Dashboard. # Inspect the side navigation and all dashboard sections. # Inspect the Total Revenue and Monthly Revenue cards for navigation. # Attempt to locate and open a dedicated revenue report. Expected Result: A link, tab, or section is available in the Admin console to open the dedicated revenue report. Actual Result: No link, tab, section, or clickable dashboard element was available to access the revenue report. Only summary revenue values were displayed. Test Type: Manual UI testing. |  | 09/Oct/26 6:45 PM | 09/Oct/26 6:45 PM
SCRUM-61 | Manual / UI | Dashboard Total Revenue omits decimal amounts from the displayed total | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Admin Dashboard & Reporting → View store overview. The dashboard must display total revenue consistently and accurately. Preconditions: # EduShop is running. # An Admin is signed in. # Orders exist with non-cancelled totals that include decimal values. Steps to Reproduce: # Open Admin → Orders and record the amount and status of each order. # Sum all non-cancelled order amounts. # Open Admin Dashboard and inspect Total Revenue. # Change order #5 with amount $75.99 from Pending to Cancelled. # Refresh the dashboard and inspect Total Revenue again. Expected Result: Total Revenue displays the exact calculated amount including decimals. Before cancellation: $1957.41. After cancelling order #5: $1881.42. Actual Result: The dashboard omitted the decimal amounts. Before cancellation, it displayed $1957 instead of $1957.41. After cancelling order #5, it displayed $1881 instead of $1881.42. Monthly Revenue displayed the correct decimal values. Test Type: Manual UI testing. |  | 09/Oct/26 6:47 PM | 09/Oct/26 6:47 PM | 09/Oct/26 6:47 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-154719.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10043
SCRUM-62 | Manual / UI | Product detail page does not provide an option for a Customer to delete their own review | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Reviews & Ratings → Delete a review. Only the review's own author, or an Admin, can delete it. Preconditions: # EduShop is running. # Customer [mustafa@gmail.com¦mailto:mustafa@gmail.com] is signed in. # The Customer has a saved review for Yoga Mat Premium. Steps to Reproduce: # Open the Yoga Mat Premium product detail page. # Locate the Customer's own saved review. # Inspect the review actions. Expected Result: The Customer can access a delete option for their own review. Actual Result: The Customer's review was displayed, but no Delete button, delete icon, or other removal option was available. Test Type: Manual UI testing. Related Test Case: SCRUM-T97 Test Case Name: Verify a Customer can delete their own review |  | 09/Oct/26 6:52 PM | 09/Oct/26 6:52 PM | 09/Oct/26 6:52 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;image-20261009-155220.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10045
SCRUM-63 | Manual / UI | Admin console does not provide an option to edit or rename an existing category | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Category Management → [Admin] Rename a category. An Admin must be able to edit an existing category to correct or rename it. Preconditions: # EduShop is running. # An Admin is signed in. # Existing categories are available. Steps to Reproduce: # Open Admin → Categories. # Inspect the available actions for an existing category. Expected Result: An Edit or Rename option is available, allowing the Admin to update an existing category. Actual Result: No Edit or Rename option was available for categories. Only the delete action was displayed, so category renaming could not be performed from the Admin console. Test Type: Manual UI testing. |  | 09/Oct/26 7:03 PM | 09/Oct/26 7:03 PM | 09/Oct/26 7:03 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Screenshot 2026-10-09 185640.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10047

## API Bugs
Bug ID | Type | Summary | Severity | Priority | Status | Description / Reproduction Evidence | Environment | Created | Updated | Attachments / Evidence References
SCRUM-64 | API | API category filter is case-sensitive and returns no products for lowercase category values | Medium | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → Search and filter products. Filtering by category name must be case-insensitive. Electronics, electronics, and ELECTRONICS must return the same matching products. Preconditions: # EduShop backend is running. # Active products exist in the Electronics category. # The API is accessible at [http://localhost:5000.¦http://localhost:5000.] Steps to Reproduce: # Send GET /api/product?Category=Electronics. # Note that the response returns 200 OK with totalCount: 6. # Send GET /api/product?Category=electronics. Expected Result: The lowercase category filter returns 200 OK with the same six Electronics products and totalCount: 6. Actual Result: The request returned 200 OK but returned an empty items array with totalCount: 0. Affected Endpoint: GET /api/product?Category=electronics Test Type: API Testing. Related Test Case: SCRUM-T113 - API - Verify product category filtering is case-insensitive |  | 10/Oct/26 3:53 PM | 10/Oct/26 3:53 PM | 10/Oct/26 3:53 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 1_Products - Category Filter - electronics (Lowercase).png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10049
SCRUM-65 | API | API accepts negative stock values when updating a product | High | Medium | To Do | Requirement: EduShop Test Backlog → Product Catalog & Discovery → [Admin] Edit a product. Editing a product must enforce the same validation as creating it. Stock must be zero or greater, and a negative Stock value must be rejected with 400 Bad Request. Preconditions: # EduShop backend is running. # An Admin access token is available. # Product ID 26 exists. Steps to Reproduce: # Send an authenticated Admin PUT request to /api/product/26. # Use valid product data with "Stock": -1. Expected Result: The API returns 400 Bad Request and does not save a negative stock value. Actual Result: The API returned 200 OK and saved the product with Stock: -1. Affected Endpoint: PUT /api/product/26 Test Type: API Testing. Related Test Case: SCRUM-T114 - API - Verify product update rejects negative stock |  | 10/Oct/26 3:58 PM | 10/Oct/26 3:58 PM | 10/Oct/26 3:58 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 2_Product Update - Negative Stock Rejected.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10051
SCRUM-66 | API | API allows Customers to submit reviews for products they have not purchased | High | Medium | To Do | Requirement: EduShop Test Backlog → Product Reviews & Ratings → Submit a review. A Customer may review only a product they have purchased in an order whose status is Delivered. Preconditions: # EduShop backend is running. # A Customer access token is available. # The Customer has no Delivered order containing Product ID 16. Steps to Reproduce: # Send a Customer-authenticated POST request to /api/review. # Use the following request data: ProductId: 16 Rating: 5 Comment: API test: customer has not purchased this product. Expected Result: The API returns 400 Bad Request with a clear message, and no review is created. Actual Result: The API returned 200 OK and created a review even though the Customer has no Delivered order containing Product ID 16. The test review was deleted afterward as test-data cleanup. Affected Endpoint: POST /api/review Test Type: API Testing. Related Test Case: SCRUM-T115 - API - Verify a Customer cannot review an unpurchased product |  | 10/Oct/26 4:04 PM | 10/Oct/26 4:04 PM | 10/Oct/26 4:04 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 3_Review - Unpurchased Product Rejected.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10053
SCRUM-67 | API | API allows an Admin to rename a category to an existing category name | High | Medium | To Do | Requirement: EduShop Test Backlog → Category Management → [Admin] Rename a category. The same duplicate-name rule that applies on category creation must apply when renaming a category. Renaming a category to a name that already exists must be rejected. Preconditions: # EduShop backend is running. # An Admin access token is available. # Category ID 2 exists with the name Clothing. # Another category already exists with the name Electronics. Steps to Reproduce: # Send an Admin-authenticated PUT request to /api/category/2. # Use a request body with Name set to Electronics. Expected Result: The API returns 400 Bad Request with a clear duplicate-name message, and Category ID 2 remains named Clothing. Actual Result: The API returned 200 OK and changed Category ID 2 from Clothing to Electronics, creating a duplicate category name. The category was restored to Clothing afterward as test-data cleanup. Affected Endpoint: PUT /api/category/2 Test Type: API Testing. Related Test Case: SCRUM-T116 - API - Verify category update rejects a duplicate name |  | 10/Oct/26 4:07 PM | 10/Oct/26 4:07 PM | 10/Oct/26 4:07 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 4 _Category Update - Duplicate Name Rejected.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10055
SCRUM-68 | API | API calculates incorrect cart subtotal and total amount for quantities greater than 10 | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Cart totals are always arithmetically correct. Every line subtotal must equal the discounted unit price multiplied by the line quantity, for any quantity from 1 to 100. The cart total must equal the sum of line subtotals. Preconditions: # EduShop backend is running. # A Customer access token is available. # The Customer cart is empty. # Product ID 2 is active with a price of 249.99, a 15% discount, and at least 49 units in stock. Steps to Reproduce: # Send a Customer-authenticated POST request to /api/cart/items. # Use the request body: ProductId: 2 Quantity: 49 # Inspect the returned cart totals. Expected Result: The discounted unit price is 212.49. For quantity 49, the line subtotal and totalAmount should be 10412.08, and totalItems should be 49. Actual Result: The API returned 200 OK with totalItems: 49, but the subtotal and totalAmount were 10199.59. This amount equals the price of 48 units instead of 49 units. Affected Endpoint: POST /api/cart/items Test Type: API Testing. Related Test Case: [117] |  | 10/Oct/26 4:11 PM | 10/Oct/26 4:11 PM | 10/Oct/26 4:10 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 5 _Cart - Add Product Up To Available Stock.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10057
SCRUM-69 | API | API allows cart quantity to exceed stock when adding to an existing cart line | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Add a product to the cart. The stock check must validate the combined quantity already in the cart plus the newly added quantity. A cart quantity must not exceed the product's current stock. Preconditions: # EduShop backend is running. # A Customer access token is available. # The Customer cart is empty. # Product ID 2 has 49 units in stock. Steps to Reproduce: # Send a Customer-authenticated POST request to /api/cart/items with ProductId 2 and Quantity 49. # Send the same request again with ProductId 2 and Quantity 2. # Inspect the returned cart. Expected Result: The second request returns 400 Bad Request with an insufficient-stock message. The cart remains at quantity 49. Actual Result: The second request returned 200 OK and increased the cart quantity to 51, exceeding the available stock of 49. Affected Endpoint: POST /api/cart/items Test Type: API Testing. Related Test Case: [118] |  | 10/Oct/26 4:14 PM | 10/Oct/26 4:14 PM
SCRUM-70 | API | API allows updating a cart item quantity beyond available stock | High | Medium | To Do | Requirement: EduShop Test Backlog → Shopping Cart → Update quantity or remove a line. The quantity set on an existing cart line must respect the product's current stock as a ceiling. Preconditions: # EduShop backend is running. # A Customer access token is available. # The Customer cart contains one unit of Product ID 2. # Product ID 2 has 49 units in stock. # The cart item ID for Product ID 2 is available. Steps to Reproduce: # Send a Customer-authenticated PUT request to /api/cart/items/{cartItemId}. # Use the request body: Quantity: 50 # Inspect the returned cart. Expected Result: The API returns 400 Bad Request with an insufficient-stock message. The item quantity remains unchanged. Actual Result: The API returned 200 OK and changed the cart item quantity to 50, exceeding the available stock of 49. Affected Endpoint: PUT /api/cart/items/{cartItemId} Test Type: API Testing. Related Test Case: [SCRUM-T119] |  | 10/Oct/26 4:16 PM | 10/Oct/26 4:16 PM | 10/Oct/26 4:16 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Bug 7_Cart Item - Quantity Above Stock Rejected.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10059
SCRUM-71 | API | Customer order retrieval returns empty userEmail and userName | Medium | Medium | To Do | Environment: EduShop API – Postman Base URL: [http://localhost:5000¦http://localhost:5000] Precondition: A Customer account has a successfully created order. The tested order ID was 9. Steps to Reproduce: # Log in as a Customer and obtain a valid access token. # Send GET /api/order using the Customer token. # Locate the created order in the response. # Send GET /api/order/9 using the same Customer token. # Check the userEmail and userName fields in both responses. Expected Result: Both endpoints return the created order with populated userEmail and userName fields in the OrderDto response. Actual Result: Both endpoints return 200 OK and the correct order details, but userEmail and userName are returned as empty strings (""). Affected Endpoints: GET /api/order GET /api/order/{id} |  | 11/Oct/26 4:22 PM | 11/Oct/26 4:22 PM | 11/Oct/26 4:21 PM;8eec7fa8-3636-4fd2-9619-ffa3ad7b7bfd;Orders - Customer Lists Own Orders.png;https://mustafamounther.atlassian.net/rest/api/3/attachment/content/10061